## Main
Confidence Infrastructure Limited
Project Name: Confidence Cement Dhaka Limited, Danga, Narsingdi.
Subject: Tentative Work Programme of 5000 TPD VRM Mill
Structure/Component | Qty. | UoM | Design Received date | Duration (Day) | Start Date | Finished Date
Shore Protection Piling work | 15000 | Meter | 2018-12-25 | 140 | 2022-02-11 | 2022-07-01
Shore Protection Pilecap work | 270 | Meter | 2018-12-25 | 60 | 2022-07-20 | 2022-09-18
Shore Protection Retaining Wall | 270 | Meter | 2018-12-25 | 90 | 2022-09-03 | 2022-12-02
RM Shed Piling | 22764 | Meter | 2022-05-30 | 150.5 | 2022-06-07 | 2022-11-04 12:00
RM Shed upto PL | 3912.5 | Cum | 2022-06-15 | 65.2083 | 2022-10-10 | 2022-12-14 05:00
5 Meter Holding Wall |  |  |  | 60 | 2022-12-15 | 2023-02-13
RM Shed Superstructure | 500 | Ton | 2022-06-30 | 90 | 2023-01-29 | 2023-04-29
Clinker Silo ø-45 m. Pilling Work (60,000 M.T Capacity) | 7500 | Meter | Done | 89.6429 | 2022-04-20 | 2022-07-18 15:26
Clinker Silo ø-45 m. Pile Foundation (Pile Cap) | 3179.25 | Cum | 2022-06-15 | 60 | 2022-06-30 | 2022-08-29
Clinker Silo ø-45 m. Wall Casting | 4168 | Cum | 2022-06-30 | 105 | 2022-09-13 | 2022-12-27
Clinker Silo ø-45 m. Bottom Slab |  |  | 2022-06-16 | 30 | 2022-09-30 | 2022-10-30
Clinker Silo ø-45 m. Roof with steel structure | 1589.625 | Sqm | 2022-07-01 | 60 | 2023-01-05 | 2023-03-06
Flyash Silo ø-22 m. Piling work (10,000 MT Capacity) | 3800 | Meter | Done | 65 | 2022-04-20 | 2022-06-24
Flyash Silo ø-22 m. Pile Cap (10,000 MT Capacity) | 455.928 | Cum | 2022-06-10 | 60 | 2022-06-15 | 2022-08-14
Flyash Silo ø-22 m. Wall Casting (10,000 MT Capacity) | 2150 | Cum | 2022-08-15 | 45 | 2022-08-21 | 2022-10-05
Flyash Silo ø-22 m. Roof | 379.94 | Sqm | 2022-08-31 | 45 | 2022-10-12 | 2022-11-26
Cement Silo ø-20 m. Piling work (20,000 MT Capacity) | 10780 | Meter | 2022-04-15 | 60 | 2022-04-25 | 2022-06-24
Cement Silo ø-20 m. Pile Foundation (20,000 MT Capacity) | 335 | Cum | 2022-06-10 | 45 | 2022-06-15 | 2022-07-30
Cement Silo ø-20 m. Wall Casting (20,000 MT Capacity) | 3700 | Cum | 2022-06-10 | 90 | 2022-08-01 | 2022-10-30
Cement Silo ø-20 m. Slab and Cone Casting (20,000 MT Capacity) | 1500 | cum | 2022-06-10 | 60 | 2022-11-05 | 2023-01-04
Cement Silo ø-20 m. Roof (20,000 MT Capacity) | 315 | Sqm | 2022-06-15 | 70 | 2022-11-06 | 2023-01-15
MS Feeding Bin for Clinker ø-7 m. Foundation (500 MT Capacity) | 1500 | Meter | 2022-06-15 | 90 | 2022-07-01 | 2022-09-29
MS Feeding Bin for Slag ø-7 m. (450 MT Capacity) | 1500 | Meter | 2022-06-15 | 90 | 2022-07-01 | 2022-09-29
MS Feeding Bin for Limestone ø-5 m. (300 MT Capacity) | 1500 | Meter | 2022-06-15 | 90 | 2022-07-01 | 2022-09-29
MS Feeding Bin for Gypsum ø-5 m. (200 MT Capacity) | 1500 | Meter | 2022-06-15 | 90 | 2022-07-01 | 2022-09-29
MS Feeding Bin for Fly Ash ø-5 m. (100 MT Capacity) | 1500 | Meter | 2022-06-15 | 90 | 2022-07-01 | 2022-09-29
VRM Substructure and superstructure | 1000 | Cum | 2022-08-15 | 75 | 2022-09-01 | 2022-11-15
Desire Draft Achievement by dredging/barge mounted long boom excavator |  |  |  | 30 | 2022-11-15 | 2022-12-15
Jetty Pile | 1800 | Cum | Done | 40 | 2022-12-20 | 2023-01-29
Jetty PileCap |  |  |  | 90 | 2023-01-15 | 2023-04-15
Jetty Superstructure |  |  |  | 45 | 2023-04-10 | 2023-05-25
Mill House Building / Feeding Foundation | 1500 | Cum | 2022-08-15 | 120 | 2022-10-01 | 2023-01-29
Main Bag House | 1600 | Cum | 2022-08-15 | 120 | 2022-10-01 | 2023-01-29
Coal Mill | 1200 | Cum | 2022-08-15 | 240 | 2022-10-01 | 2023-05-29
Packing Section | 2100 | Cum | 2022-08-15 | 120 | 2022-10-01 | 2023-01-29
Compressor room / Water reservior | 750 | Cum | 2022-09-15 | 90 | 2022-11-15 | 2023-02-13
Office Building -6 storied | 3000 | Cum | Done | 180 | 2022-05-10 | 2022-11-06
Substation Building -2 storied | 1450 | Cum | 2022-09-20 | 100 | 2022-11-30 | 2023-03-10
Store Building -2 Storied | 1050 | Cum | 2022-08-20 | 90 | 2022-09-01 | 2022-11-30
Truck workshop -Single Storied | 1200 | Cum | 2022-09-20 | 75 | 2022-12-20 | 2023-03-05
Security, Vat Office -2 storied | 900 | Cum | 2022-09-20 | 75 | 2022-12-20 | 2023-03-05
Coal shed 2000 MT Capacity | 1200 | Cum | 2022-09-30 | 120 | 2022-12-01 | 2023-03-31
Maintance Work-shop (180 m²) | 450 | Cum | 2022-09-20 | 90 | 2022-06-25 | 2022-09-23
33KV Powerline construction and power connection |  |  |  | 360 | 2022-09-01 | 2023-08-27
Foundation and steel works for support structures |  |  |  | 150 | 2022-09-30 | 2023-02-27
Ancillary Works ( Boundary wall, landscaping,levelling and dressing,internal road, drain network |  |  |  | 370 | 2022-04-01 | 2023-04-06
N.B:- Eid Ul Fitre Vacation from 1st May,2022 to 15th May,2022 and Eid Ul azha Vacation from 5th July to 20th July,2022
Eid Ul Fitre Vacation from 18th April,2023 to 30th April,2023 and Eid Ul azha Vacation from 25th June to 10th July,2023 is considered in the above tentative work schedule
Special Note:- The above Schedule will be possible on the availibility of drawing.
Formulas:
Finished Date = [Start Date]+[Duration (Day)]
Finished Date = [Start Date]+45
Start Date = [Finished Date, row above]-15
Start Date = [Finished Date, row above]+15